Working document:

Courtesy working document of the Application Form – Urban Innovative Actions (UIA)

3rd CALL FOR PROPOSALS

Please note that this document is only a working document whose purpose is solely in helping applicants to develop their Application Form.

This document will not be considered as a formal Application Form.

Only Application Forms submitted through the online Electronic Exchange Platform (EEP), will be considered by the Permanent Secretariat.

Please note that the working version here below represents a simplified version of the full Application Form template available in the EEP. Furthermore, there is no guarantee that this version corresponds 100% to the latest official version included in the EEP. You are strongly encouraged to login in to the EEP as early as possible. Do not wait until the last few days of the Call.

Please read the Call Terms of Reference and UIA Guidance before starting to complete the Application Form.

Character limits are to be considered including spaces. Furthermore, some elements of the Application Form will be automatically generated in the EEP. However it may help projects to fill them in the working document to have the complete overview of the project.

As a final reminder to all applicants, please bear in mind that a panel of external experts will assess submitted projects therefore information included in the application form should provide detailed, easy to grasp concepts that can be understood by someone not completely familiar with the specific context and challenges of your urban area.

Examples have been included in this document in order to help the reader’s understanding. These examples are purely illustrative.

PART A – Project Summary

A.1 Project identification

| Project acronym |  | [30 characters] |
| --- | --- | --- |
| Project title |  | [250 characters] |
| Project number |  | Automatically generated when project is saved for the 1st time. |
| Name of the Main Urban Authority |  | (automatically filled in) |
| ERDF rate |  | Max 80% |
| Project duration | Start date | (date of the project approval as defined in the Terms of Reference for the Call for Proposals) |
|  | End date | Max 3 years after start date |
|  | Total number of months | Automatically calculated |
| Topic |  | Drop-down menu with topics related to the specific Call for Proposals. Applicants are requested to select only one of the topics proposed for each Call for Proposals. However, in section C.1.5 of the Application Form “Integrated Approach”, applicants can describe linkages and externalities with other topics. |

A.2 Project summary

- Project Summary description

[1500 Characters] Briefly and clearly describe the challenge (1) to be addressed, the proposed solution (2), why it is original and innovative (3) as well as the change (4) you want to make to the actual situation (i.e. the expected result)

Table automatically generated from the Work Plan

|  | Budget – breakdown per funding sources and partners |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Partner | Country | ERDF co-financing 80% |  | Contribution 20% Partners need to secure public or private contributions to complete their budget with at least 20% of the TEC |  |  | Total 100% |  |
| Partner |  | EUR | ERDF rate | Public | Private | Total | Budget | % of project budget |
| PP1 |  |  |  |  |  |  |  |  |
| PP2 |  |  |  |  |  |  |  |  |
| … | … |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |

PART B – Partnership

Partnership - Summary table

Relevance of the partnership

[1000 Characters] Why is the proposed partnership relevant to deliver the proposed innovative solution? Describe how the proposed partnership (Main (and Associated if relevant) Urban Authority(ies) and Delivery Partners supported by the wider group of stakeholders) demonstrates a good horizontal and vertical integration and is balanced and complementary for a successful implementation of the UIA project.

The Urban Authority(ies) involved represent(s) XXXX inhabitants (the total number of inhabitants comes from Urban Authority(ies)’s profile(s) and is automatically aggregated here)

Table automatically generated from partners’ profiles

| Role | Name of organisation | Country |
| --- | --- | --- |
| Urban Authority | XXX | x |
| Associated Urban Authority | YYY | x |
| Delivery Partner | ZZZ | x |
| Delivery Partner | WWW | x |

B.1

| Main Urban Authority |  |
| --- | --- |
| Name of organisation |  |
| Member State |  |
| Number of inhabitants | Applicants shall report the figures indicated the following Correspondence Table from EUROSTAT/ Urban Audit database: Correspondence table LAU2-NUTS2010, EU28 (2012): http://ec.europa.eu/eurostat/web/nuts/local-administrative-units. Column I of the tab dedicated to each Member State |
| Comments | If more recent official census figures are available, you can use these and provide the official source of the more recent figures (e.g. national census from 2015). In case of organised agglomeration applying as Main Urban Authority, please list all the constituting municipalities of the organised agglomeration. For Urban Authorities located in United Kingdom, Ireland, Portugal, Lithuania and Greece, please also list all the constituting wards (UK), electoral districts (Ireland), parishes (Portugal), elderships (Lithuania) or former municipalities (before the territorial reform). For more information regarding these cases, please refer to section 1.4.1 of the UIA Guidance. |
| Department(s)/unit(s)/division(s) concerned | [500 Characters] List here the departments, units and divisions that will be involved in the implementation of the project. For each department/unit/division provide information on the specific role in the implementation phase as well as the name of person to be involved and their position within the department/unit/division. |
| Contact person, legal representative and contact details | Provide the name, title and contact details of the person who will serve as project main contact person. This person will be the main contact person for the Permanent Secretariat during the implementation of the project. Provide the name, title and contact details of the legal representative of the (Main) Urban Authority. Be aware that the two contacts listed here will be the only ones receiving notifications from the Permanent Secretariat during the selection process. |
| VAT number |  |
| VAT recoverable | Drop down menu with: yes, no, partly |
| Staff costs claimed on the basis of: | Real costs For more information about staff costs, please refer to section 4.2 of the UIA Guidance. |
| Involvement in the design phase | [500 Characters]. Describe the main contributions of the Main Urban Authority in the design phase. Describe the coordination mechanisms set up to ensure the involvement of the different departments of the Main Urban Authority in the design of the project proposal. |
| Involvement in the implementation phase | [750 Characters] Describe the contribution the MUA will bring to the project implementation and indicate the WPs (activities) where it is involved to check their competencies and expertise relevance (also useful for cross references). |
| Competences and experiences in relation to the challenge addressed? | [500 Characters] Describe the main legal and operational competencies (e.g. does your urban authority have powers over the policy it would like to tackle?) and experience of the organisation in relation to the challenge addressed and to the proposed project. Demonstrate that the applying organisation is the best placed to implement the project. |
| Experience in participating in and/or managing EU co-financed projects or other international projects. | [500 Characters] If applicable, describe the main experience of the organisation in participating and/or managing EU co-financed projects or other international projects. Please remember to list those projects that are of relevance to the topic addressed as well as the programmes that have funded them. Provide information on the role of the organisation in the projects listed (Lead Partner, partner, observer, etc.) |

Total Partner Budget

| PROGRAMME CO-FINANCING 80% |  | CONTRIBUTION 20% |  |  | TOTAL (€) |
| --- | --- | --- | --- | --- | --- |
| ERDF (€) (a) | ERDF Co-financing rate (%) | Public Contribution (€) (b) | Private Contribution (€) (c) | Total Contribution (€) (d)=(b)+(c) | Total Eligible Cost (€) (e)=(a)+(d) |

Breakdown of Partner Budget per Work Package/ Budget Line

Table automatically generated from the Work Plan

| Work Package | Staff Costs (€) | Office and Administration (€) | Travel and Accommodation (€) | External Expertise and services (€) | Equipment (€) | Infrastructure and works (€) | Sub-total (€) | Revenues (€) | Total (€) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP1 |  |  |  |  |  |  |  |  |  |
| WP2 |  |  |  |  |  |  |  |  |  |
| WP3 |  |  |  |  |  |  |  |  |  |
| WP4 |  |  |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |  |  |
| Total (€) |  |  |  |  |  |  |  |  |  |
| % of total budget |  |  |  |  |  |  |  |  |  |

B.2

+ Add button (to add associated urban authorities)

- In the case of associations or groupings of urban authorities having a legal status of organised agglomeration, only the organised agglomeration shall be listed in the section B.1 as Main Urban Authority - In the case of associations or groupings of urban authorities without a legal status of organised agglomeration or grouping of urban authorities willing to apply jointly, applicants shall identify and list one urban authority as the Main Urban Authority (section B.1) and the other urban authorities as Associated Urban Authorities (section B.2 below) - For detailed information on the eligible urban authorities and more especially on the organisations recognised as organised agglomerations in the framework of the UIA Initiative, please check the UIA Guidance, section 1.4. For detailed information on the roles and responsibilities of Associated Urban Authorities (and Delivery Partners) please check the UIA Guidance, section 2.1.

| Associated Urban Authority |  |
| --- | --- |
| Name of organisation |  |
| Member State |  |
| Number of inhabitants | Applicants shall report the figures indicated by Eurostat in the following table from EUROSTAT/ Urban Audit database: Correspondence table LAU2-NUTS2010, EU28 (2012): http://ec.europa.eu/eurostat/web/nuts/local-administrative-units . Column I of the tab dedicated to each Member State |
| Comments | If more recent official census figures are available, you can use these and provide the official source of the more recent figures (e.g. national census from 2015). In case of organised agglomeration applying as Main Urban Authority, please list all the constituting municipalities of the organised agglomeration. For Urban Authorities located in United Kingdom, Ireland, Portugal, Lithuania and Greece, please also list all the constituting wards (UK), electoral districts (Ireland), parishes (Portugal), elderships (Lithuania) or former municipalities (before the territorial reform). For more information regarding these cases, please refer to section 1.4.1 of the UIA Guidance. |
| Department(s)/unit(s)/division(s) concerned | [500 Characters] List here the departments, units and divisions that will be involved in the implementation of the project. For each department provide information on the specific role in the implementation phase as well as the name of person to be involved and their position within the department |
| Contact person, legal representative and contact details | Provide the name, title and contact details of the person who will serve as main reference within the organisation during the implementation of the project. Provide the name, title and contact details of the legal representative of the Associated Urban Authority. |
| VAT number |  |
| VAT recoverable | Drop down menu with: yes, no, partly |
| Staff costs claimed on the basis of: | Real costs For more information about staff costs, please refer to section 4.2.1 of the UIA Guidance. |
| Involvement in the design phase | [500 Characters] Describe the coordination mechanisms set up to ensure the involvement of the Associated Urban Authority in the design of the project proposal. Describe the main contributions of the Associated Urban Authority in the design phase. |
| Involvement in the implementation phase | [750 Characters] Describe the contribution the partner will bring to the project implementation and indicate the WPs (activities) where it is involved to check their competencies and expertise relevance (also useful for cross references). |
| Competences and experiences in relation to the challenge addressed | [500 Characters] Describe the main reasons why the Associated Urban Authority will be involved in the implementation of the project (specific competencies and expertise). Describe the main legal and operational competencies and experience of the organisation in relation to the challenge addressed and to the proposed project. Demonstrate that the Associated Urban Authority is the best placed to implement the project. |
| Experience in participating in and/or managing EU co-financed projects or other international projects. | [500 Characters] If applicable, describe the main experience of the organisation in participating and/or managing EU co-financed projects or other international projects. Please remember to list those projects that are of relevance to the topic addressed as well as the programmes that have funded them. Provide information on the status of the organisation in the projects listed (Lead Partner, partner, observer, etc.) |

Total Partner Budget

| PROGRAMME CO-FINANCING 80% |  | CONTRIBUTION 20% |  |  | TOTAL (€) |
| --- | --- | --- | --- | --- | --- |
| ERDF (€) (a) | ERDF Co-financing rate (%) | Public Contribution (€) (b) | Private Contribution (€) (c) | Total Contribution (€) (d)=(b)+(c) | Total Eligible Cost (€) (e)=(a)+(d) |

Breakdown of Partner Budget per Work Package/ Budget Line

Table automatically generated from the Work Plan

| Work Package | Staff Costs (€) | Office and Administration (€) | Travel and Accommodation (€) | External Expertise and services (€) | Equipment (€) | Infrastructure and works (€) | Sub-total (€) | Revenues (€) | Total (€) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP1 |  |  |  |  |  |  |  |  |  |
| WP2 |  |  |  |  |  |  |  |  |  |
| WP3 |  |  |  |  |  |  |  |  |  |
| WP4 |  |  |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |  |  |
| Total (€) |  |  |  |  |  |  |  |  |  |
| % of total budget |  |  |  |  |  |  |  |  |  |

B.3

+ Add button (to add Delivery Partners)

| Delivery partners |  |
| --- | --- |
| Name of organisation |  |
| Member State |  |
| Partner description and department/unit/division concerned | [500 Characters] Provide a description of the organisation and list the departments, units and divisions that will be involved in the implementation of the project. For each department provide information on the specific role in the implementation phase as well as the name of person to be involved and their position within the department |
| Contact person, legal representative and contact details | Provide the name, title and contact details of the person who will serve as main reference within the organisation during the implementation of the project. Provide the name, title and contact details of the legal representative of the Delivery Partner. |
| VAT number |  |
| VAT recoverable | Drop down menu with: yes, no, partly |
| Staff costs claimed on the basis of: | Real costs For more information about staff costs options, please refer to section 4.2.1 of the UIA Guidance. |
| Involvement in the design phase | [500 Characters] Describe the coordination mechanisms set up to ensure the involvement of the Delivery Partner in the design of the project proposal. Describe the main contributions of the Delivery Partner in the design phase. |
| Involvement in the implementation phase | [750 Characters] Describe the contribution the partner will bring to the project implementation and indicate the WPs (activities) where it is involved to check their competencies and expertise relevance (also useful for cross references). |
| Competences and experiences in relation to the challenge addressed | [500 Characters] Describe the main reasons why the Delivery Partner will be involved in the implementation of the project (specific competencies and expertise). Describe the main legal and operational competencies and experience of the organisation in relation to the challenge addressed and to the proposed project. Demonstrate that the Delivery Partner is the best placed to implement the project. |
| Experience in participating in and/or managing EU co-financed projects or other international projects. | [500 Characters] If applicable, describe the main experience of the organisation in participating and/or managing EU co-financed projects or other international projects. Please list those projects that are of relevance to the topic addressed as well as the programmes that have funded them. . Provide information on the role of the organisation in the projects listed (Lead Partner, partner, observer, etc.) |

Total Partner Budget

| PROGRAMME CO-FINANCING 80% |  | CONTRIBUTION 20% |  |  | TOTAL (€) |
| --- | --- | --- | --- | --- | --- |
| ERDF (€) (a) | ERDF Co-financing rate (%) | Public Contribution (€) (b) | Private Contribution (€) (c) | Total Contribution (€) (d)=(b)+(c) | Total Eligible Cost (€) (e)=(a)+(d) |

Breakdown of Partner Budget per Work Package/ Budget Line

Table automatically generated from the Work Plan

| Work Package | Staff Costs (€) | Office and Administration (€) | Travel and Accommodation (€) | External Expertise and services (€) | Equipment (€) | Infrastructure and works (€) | Sub-total (€) | Revenues (€) | Total (€) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WP1 |  |  |  |  |  |  |  |  |  |
| WP2 |  |  |  |  |  |  |  |  |  |
| WP3 |  |  |  |  |  |  |  |  |  |
| WP4 |  |  |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |  |  |
| Total (€) |  |  |  |  |  |  |  |  |  |
| % of total budget |  |  |  |  |  |  |  |  |  |

PART C – Project description

C.1 Project relevance and innovativeness

C.1.1 Main challenge(s) to be addressed

[3000 Characters] What is the main urban challenge(s) that will be tackled by the project? Explain why you chose to address this challenge. Include a short description of the context of the urban area by describing the extent of the challenge to be addressed, its breadth and depth at local level (using data and other evidence - e.g. employment rate, % of migrants/refugees, % of greenhouse emission, etc.) and its different dimensions (social, economic and environmental dimensions of the challenge).

C.1.2 Proposed solution

[3000 Characters] Describe the solution (i.e. the innovative action/s) you propose in order to tackle the main challenges identified above. Describe clearly the proposed solution/project (presenting the main strands of activities proposed) and explain why and how you think it will address the challenge(s) identified in part C.1.1. When describing the action(s) proposed, ensure to make clear references to the Work Packages and main actions described in the Work Plan. Experts in charge of the Strategic Assessment should be able to understand the main elements of your project when reading this section.

C.1.3 Innovativeness of the proposed solution

[3000 Characters] - Explain to what extent the project proposal is a new solution and can add value in relation to the issue concerned. - Demonstrate that the solutions proposed (and its main components) have not been previously tested and implemented on the ground in the urban area concerned and elsewhere in Europe. Please remember, the innovativeness of the project has the largest weight in the assessment of the project (40% of the scoring) In order to fill in this section, urban authorities are requested to carry out a benchmark analysis of existing good practices (in Europe and beyond) in the policy area concerned in order to explain how and to what extent the proposed solution is different from existing good practices and how and to what extent it will build upon these. The benchmark should include at least 3 references of existing good practices taken into account. Existing online databases (e.g. CORDIS for Framework Programmes, IEE and LIFE projects database etc.) and cities’ networks best practices and working groups (e.g. URBACT, Eurocities, Energy Cities, etc.) are potential relevant sources of information to carry out your benchmark. More especially, when filling in this section, please take into account: - The elements of the proposed project described in C.1.2 that are new and innovative vis-a-vis: (1) policies/programmes already in place in your city addressing similar challenges, (2) similar policies/programmes in other cities in Europe and beyond - Focus and expand on the elements of the proposed project that set it apart from existing policies and/or practices at local level as well as from similar policies/programmes in other cities in the EU. - Describe whether the approach for your project evolved over time based on lessons learned from experience and existing good practices (evolutionary approach – the innovation lies in the new elements added to the idea) or if it is a completely new approach (or an approach borrowed from elsewhere outside Europe) never tried before in the sector or context in question (revolutionary approach).

C.1.4 Potential obstacles and resistance

[1500 Characters] Describe whether you expect any obstacles (e.g.: national or legal framework, changing financial and political conditions, etc.) or resistance (e.g.: lack of political will, opposition from organised groups of inhabitants, etc.) to the implementation of the innovative solutions proposed and if so, how they will be overcome. Please do not list here the risks related to the project implementation and management as this will be done in Part F (risks management).

C.1.5 Integrated approach

[1500 Characters] To what extent is the solution proposed an integrated solution? Describe how the proposed project will address the different dimensions of the challenge, as described in section C.1.1. Describe what are the links and externalities (positive and negative) with other policy areas addressed (directly or indirectly) by the proposed solution. For more information on the concept of integrated approach for sustainable urban development, applicants can check the website of the DG Regional and Urban Policy where the following definition can be found: “The various dimensions of urban life – environmental, economic, social and cultural – are interwoven and success in urban development can only be achieved through an integrated approach. Measures concerning physical urban renewal must be combined with those promoting education, economic development, social inclusion and environmental protection. It also calls for strong partnerships between local citizens, civil society, industry and various levels of government (ministries, regional and/or provincial authorities, etc.)”.

C.1.6 Link to ERDF Thematic Objectives and Investment Priorities

[1500 Characters] How does the project support the ERDF Thematic Objectives and Investment Priorities? List here the ERDF Thematic Objectives and Investment Priorities (you can find the full list in article 5 of the ERDF regulation 1301/2013) that the proposed project is expected to contribute to. Explain clearly how the project will contribute to these. Given the expected integrated nature of the project proposed, several Thematic Objectives and Investment Priorities can be listed here. Please include the Thematic Objectives (TO) and Investment Priorities (IP) number (e.g. TO3 / IP.3.a, TO9 / IP.9.f) in your explanation for easier understanding.

C.2 Project context and local partnership

C.2.1 Link with other local/regional/national strategies and policies (incl. smart specialisation strategies)

[1500 Characters] Is the project part of wider local/regional/national strategies and policies? List and describe any other local/regional/national strategies and policies already in place at local level addressing the identified challenge. Explain how the existing policies/strategies will be taken into account by the proposed project. In particular, please, identify the elements that will be re-used and/or improved and the synergies that will be created. Please make sure to mention the potential links with and expected contribution (if existing) to your regional/national smart specialisation strategy.

C.2.2 Synergies with other projects and initiatives

[1500 Characters] What are the synergies with past or current EU and other local projects or initiatives the project makes use of? Describe any other projects and initiatives (EU funded or not) already implemented at local level to address the identified challenge. Explain how the projects/initiatives identified will be taken into account by the proposed UIA project, in particular identify the elements that will be re-used and/or improved. Describe the synergies with other ongoing projects dealing with similar issues, if any.

C.2.3 Involvement of wider stakeholders in project design

[2000 Characters] Who are the wider stakeholders involved in the preparation and design of the project? How have they been involved? Provide a list of the wider stakeholders (not including the Associated Urban Authorities and Delivery Partners mentioned in Part B) that have been involved in the design of the proposed project. Describe the coordination/consultation/co-design mechanisms you have set up to ensure their involvement in the design phase. (e.g. how have they been consulted? Has a meeting been held? When did the consultation and co-design start?). Present the main contributions made by the wider group of stakeholders during the project design.

C.2.4 Involvement of wider stakeholders in project implementation:

[2000 Characters] Who are the wider stakeholders that will be involved in the implementation of the project? How will they be involved? Provide a list of the wider stakeholders (the Main/Associated Urban Authorities and Delivery Partners mentioned in Part B should not be listed here) that will be involved in the implementation of the project. Clearly describe the coordination/consultation/co-implementation mechanisms to be set up to ensure their involvement in the implementation phase (i.e. how will they be involved once the project starts?). Please state in which work packages the wider stakeholder group will be involved and present the main contributions during the implementation phase.

C.3 Project objectives, results and outputs

C.3.1 Overall objectives and expected results (changes in the local situation)

In the 2014-2020 programming period, Cohesion Policy pursues a result-oriented framework in order to better contribute to the Europe 2020 Strategy. As under most Cohesion Policy Programmes and initiatives for the 2014 – 2020 programming period, UIA projects are requested to work in a result-oriented framework and to demonstrate it in their Application Form through the use of the intervention logic model. This section (and the later declination of the intervention logic into concrete activities, deliverables and outputs in the work plan section) therefore builds on a number of building blocks (objectives, results, outputs, indicators) and terms related to the result-oriented framework. For more information about these building blocks and terms and what these mean for urban authorities, you can refer to the URBACT Guide - Applying the results framework to Integrated Actions Plans.

PROJECT main objective(s)

[2000 characters] Describe the main objective (s) you want to achieve through the proposed project.

PROJECT main result(s)

[2000 characters] Describe the change in the local situation that you want to see as a consequence of the project. Describe how the local situation will look like if the project is successful. Bear in mind that results should be realistic, specific, concrete and measurable.

C.3.2 Outputs

Table of outputs automatically generated from the Work Plan (investment included)

| WP (number + name) | Output Number | PROJECT output | Target value of PROJECT expected output(s) |
| --- | --- | --- | --- |
| WP x _ YYYYY | O.X.X.X | Project Output X [250 characters] Please be reminded an output is what has actually been produced for the money given to the project. It shall be captured by an output indicator, and directly contributes to the achievement of the project result. | The target value provides the expected quantity of the output. This shall not be confused with the number of beneficiaries using the output |
|  | O.X.X.X | Project Output Y [250 characters] |  |
|  | O.X.X.X | Project Output Z [250 characters] |  |
| WPx Investment | I.X.X | Project Output Z [250 characters] |  |

C.3.3 Measurement of results

[2000 Characters] For each result listed in section C.3.1, provide information on the main indicators and target values to measure them. Through this section, applicants should be able to demonstrate that the change in the local situation is directly attributable to the proposed new approach and not to external factors.

C.3.4 Methodology for monitoring and measurement of outputs and results

[2000 Characters] Describe the methodology (how) and tools you will use to collect and measure data to monitor expected outputs and results (e.g. collection of data from street sensors, qualitative surveys, randomised control trials, etc.). Explain when you will first be able to measure the results of your project at local level. Results indicators should only be mentioned in the section C.3.3.

C.3.5 Target groups

[2000 Characters] Specify who are the main target groups (e.g. young unemployed people, SMEs, asylum seekers, etc.) for the proposed project and how they will benefit from the expected outputs and results. Where possible, please also indicate how many persons from each target group will benefit from the project outputs and results. Please include all target groups mentioned in the different project work packages.

C.4 Project scaling up and transferability

C.4.1. Scaling up of the project

[2000 characters] Describe how you envisage to scale up the project if it is successful. Can the proposed solution be applied in other parts of the city? At a larger scale? Are there already plans for scaling up? What type of resources (human, political, financial) will be needed to scale up the project to other neighbourhoods or to the entire urban area? What could be the indicative calendar for the scaling up process?

C.4.2 Transferability of the project: evidence of demand for your project in other cities

[2000 characters] - Explain why the challenge addressed and the solution proposed will be relevant for other urban authorities in Europe. - Explain why the project can be transferred and replicated by other Urban Authorities in different local context. (what are the material and immaterial conditions and resources that other urban authorities should ensure in order to replicate the project locally) - Describe the mechanisms that could facilitate the transfer of the practice to other urban authorities in Europe (e.g. networking initiative such as URBACT, publications, etc.).

References (not mandatory)

[2000 characters] This non-mandatory section enables you to provide the Permanent Secretariat and the Panel of External Experts in charge of the strategic assessment of your proposal with internet addresses should you wish to make reference to certain information. It could for instance be a link to an existing and complementary initiative to the proposed project, or further information about a technical solution the project wishes to implement. Describe briefly the reasons and the relevance of the information related to each internet address.

PART D – Work plan

| WP nr. | Title | Work Package type | Start date | End date |
| --- | --- | --- | --- | --- |
| 1 | Preparation | Preparation | MM.YYYY | MM.YYYY |
| 2 | Project Management | Project Management |  |  |
| 3 | Communication | Communication |  |  |
| 4 | Implementation of a work package | Implementation |  |  |
| 5 | Investment WP | Investment |  |  |
| 6 | Closure and knowledge transfer | Closure |  |  |

The work plan is structured around work packages. Each work package is then organised into activities which lead to deliverables and outputs. You can find below a definition of these different work plan elements.

- An activity is a specific task performed for which resources are used. Be aware that max. 5 activities can be listed per implementation work package. Each activity shall result in a deliverable and/or an output.

- A deliverable is a tangible or intangible object delivered as a side-product of the project and/or an intermediary step in the delivery of a project output. Deliverables shall therefore directly contribute to the achievement of a project output. Deliverables should also reflect relevant steps of a single activity.  In general terms 2 or more deliverables are necessary to produce a project output.

- An output is what has actually been produced as a result of the funding given to the project and is a main product of the project. It shall directly contribute to the achievement of project result(s). Each Work package should lead to the delivery of at least one output.

Activities, deliverables and outputs should include a clear description of what would be achieved in each individual element, reflect the link between them as well as the relevance to the different work packages (and therefore  to the overall work plan.

Applicants are strongly invited to include explicit cross-references in order to facilitate the understanding of links and complementarities among activities and Work Packages. Cross-references are essential in order to provide a clear view on the project intervention logic.

Please mention which partner/s will be involved in/responsible for the delivery of the activities/outputs/deliverables. Partners’ involvement should also be reflected in their budget description.

For each activity, describe the main intermediary steps (and corresponding delivery months) necessary for achieving the proposed outputs/results. Pay attention to the logical time sequence between the different activities/deliverables/work packages. If the deliverable is of a repetitive nature (i.e. newsletter) please include the last delivery date. In the description specify the start date and when they are expected to be delivered in between (i.e. month 3 – month 4).

Bear in mind that target values that you will indicate for deliverables and outputs should capture the quantity of deliverables/outputs produced, not the expected number of beneficiaries. For example, the target value for a series of training workshops would be 20 (if 20 workshops are foreseen), whereas the number of beneficiaries (e.g. 450 people) should be indicated in the description of the corresponding activity/deliverable.

| WP nr. | WP title |  | Start date | End date | WP budget |
| --- | --- | --- | --- | --- | --- |
| 1 | Project preparation Read-only WP, no modifications are possible – prefilled start and end date and lump sum |  | MM.YYYY | MM.YYYY | EUR 20,000 |
| Partners’ involvement |  |  |  |  |  |
| WP responsible partner |  | Main Urban Authority |  |  |  |
| Summary |  |  |  |  |  |
| Preparation and submission of the application form |  |  |  |  |  |

Work Package Budget

| Partner name | Staff cost (€) | Office and Administration (€) | Travel and Accommodation (€) | External Expertise and services (€) | Equipment (€) | Infrastructure and works (€) | Sub-total (€) | Revenues (€) | Total (€) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| WP Nr. | WP title |  | Start date | End date |  |  | WP budget |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2 | Project management |  | Automatic from activities | Automatic from activities |  |  | Automatic |  |  |
| Partners’ involvement |  |  |  |  |  |  |  |  |  |
| WP responsible partner |  |  |  |  |  |  |  |  |  |
| Other involved partners |  |  |  |  |  |  |  |  |  |
| Summary |  |  |  |  |  |  |  |  |  |
| [1500 characters] Describe how the management on the strategic and operational level will be carried out in the project, specifically: - structure, responsibilities and procedures for the day to day management and coordination (including whether it is foreseen to externalise the management) - communication and decision-making within the partnership (e.g. steering group) - coordination mechanism with the wider group of stakeholders - reporting (including financial – costs related to auditors should not be included in the budget as the UIA will provide the project with a First Level Controller) and evaluation procedures - risk and quality management - Capitalisation Please note that one activity has to be exclusively devoted to capitalisation activities (capturing knowledge and drawing lessons on an ongoing basis). These include the involvement of UIA experts during project implementation. Up to 50 days of expert involvement will be allocated to each project depending on a need analysis. The costs for expertise (including travel and accommodation) will be covered directly by the UIA Initiative. |  |  |  |  |  |  |  |  |  |
| Activities and deliverables |  |  |  |  |  |  |  |  |  |
| Activity A. 1.1 | Activity title: |  |  |  |  | Start date (MM.YYYY) |  |  | End date (MM.YYYY) |
|  | Activity description and partners involved [750 characters] Typical activities for this work package are for instance: - Internal communication within the partnership - Project control and reporting - Coordination of the partnership - Coordination with the wider group of stakeholders - Monitoring and evaluation Please mention which partner/s will be involved in the activity. Example: A.2.1 Management and coordination (the description provided will mention the intermediary steps justifying the whole activity logic, these steps will be reflected as deliverables structured in a logical chain). |  |  |  |  |  |  |  |  |
| D 1.1.1 | Deliverable description [250 characters] The deliverables of the activity mentioned above would be: D.2.1.1 Coordination steering committee meetings D.2.1.2 Implementation working group meeting D.2.1.3 Stakeholder group meeting |  |  |  |  | Target value |  |  | Delivery date (MM.YYYY) |
| Activity A.1.N | Activity title: Capitalisation |  |  |  |  | Start date (MM.YYYY) |  |  | End date (MM.YYYY) |
|  | Activity description and partners involved 1) Involvement of UIA Experts for: - Advice and guidance on the substance of the action, especially regarding the innovative content - Assistance in the development of documentation and outputs that will capture and disseminate lessons learnt, good practices, etc. To the wide European audience - Support to ensure that the action remains on track and is in line with the agreed proposal 2) Participation to the activities of the Urban Development Network 3) Participation to national/international conferences to share lessons learnt and good practice on ongoing basis |  |  |  |  |  |  |  |  |
| D.1.N | Deliverable - Thematic deliverables produced by UIA Experts on ongoing basis - Other deliverables related to capitalization activities |  |  |  | Target value |  |  | Delivery date (MM.YYYY) |  |

Work Package Budget

Please detail the planned costs under the different budget lines at partner level, specifying how the money will be spent. Costs descriptions should enable a clear reconciliation with the activities proposed in the work plan.

| PP1 - Name | Staff cost (€) | Office and Administration (€) | Travel and Accommodation (€) | External Expertise and services (€) | Equipment (€) | Sub-total (€) | Revenues (€) | Total (€) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | [250 characters] Please detail the planned costs. Further information on the eligible costs under this budget line is to be found in the UIA guidance under section 4 For example: Management and coordination of the project by 1 full time project manager and 0.5 part time project assistant for the organization of all project events and meetings. Director will also be involved in steering committee. | Office and administration costs are covered by a flat rate (15%). No description is therefore needed (the EEP system will automatically indicate N/A). Further information on the eligible costs under this budget line is to be found in the UIA guidance under section 4 | [250 characters] Further information on the eligible costs under this budget line is to be found in the UIA guidance under section 4 For example: Participation to 3 meetings of the steering committee per year. | [250 characters] Further information on the eligible costs under this budget line is to be found in the UIA guidance under section 4 For example: Financial manager hired, catering for Steering Committee events … | [250 characters] Further information on the eligible costs under this budget line is to be found in the UIA guidance under section 4 For example: Cost for 3 laptops … | Automatically calculated | [250 characters] Further information on the eligible costs under this budget line is to be found in the UIA guidance under section 4. | No explanation requested |
| Amount (€) |  |  |  |  |  |  |  |  |
| PP2 – Name | Staff cost (€) | Office and Administration (€) | Travel and Accommodation (€) | External Expertise and services (€) | Equipment (€) | Sub-total (€) | Revenues (€) | Total (€) |
| Description | See above | See above | See above | See above | See above |  | See above |  |
| Amount (€) |  |  |  |  |  |  |  |  |
| PP3 – Name | Staff cost (€) | Office and Administration (€) | Travel and Accommodation (€) | External Expertise and services (€) | Equipment (€) | Sub-total (€) | Revenues (€) | Total (€) |
| Description | See above | See above | See above | See above | See above |  | See above |  |
| Amount (€) |  |  |  |  |  |  |  |  |
| PP…X – Name | Staff cost (€) | Office and Administration (€) | Travel and Accommodation (€) | External Expertise and services (€) | Equipment (€) | Sub-total (€) | Revenues (€) | Total (€) |
| Description | See above | See above | See above | See above | See above |  | See above |  |
| Amount (€) |  |  |  |  |  |  |  |  |
| Total (€) | Automatically calculated | Automatically calculated | Automatically calculated | Automatically calculated | Automatically calculated | Automatically calculated | Automatically calculated | Automatically calculated |

| Indicative budget breakdown per year |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Year | 2018 | 2019 | 2020 | 2021 | Total |
| % budget |  |  |  |  | 100% |
| Amount |  |  |  |  |  |

| WP Nr | WP title |  |  | WP start date | WP end date |  | WP budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3 | Communication |  |  | Automatic from activities | Automatic from activities |  | Automatic |  |
| Partners’ involvement |  |  |  |  |  |  |  |  |
| WP responsible partner |  |  |  |  |  |  |  |  |
| Other involved partners |  |  |  |  |  |  |  |  |
| Summary |  |  |  |  |  |  |  |  |
| [1500 characters] Describe the communication strategy and the way it will contribute to achieving the project’s objectives. Please describe clearly the communication objectives for each of the identified target groups (outreach and engagement actions), together with the relevant communication activities. When describing this work package activities, cross-references with the other work packages should be made where possible to better understand how communication plays a role and supports the implementation of the core activities. |  |  |  |  |  |  |  |  |
| Communication Objectives What can communication do to reach the project objectives? |  |  |  | Target groups List who you need to reach |  |  |  |  |
| [500 characters] |  |  |  | [500 characters] Where possible, please also indicate the expected number of target groups you aim to reach. |  |  |  |  |
| Activities and deliverables Please see examples, full description and recommendations for activities and deliverables made in work package 2. |  |  |  |  |  |  |  |  |
| Activity number |  | Activity title, description and partners involved |  |  |  | Start date |  | End date |
| A 3.1 |  | Activity description and partners involved [750 characters] Start-up activity |  |  |  | Start date (MM.YYYY) |  | End date (MM.YYYY) |
| D 3.1.1 |  | Deliverable |  |  |  | Target value |  | Delivery date(MM.YYYY) |
| A.3.2 |  | Activity description and partners involved [750 characters] Publications |  |  |  | Start date (MM.YYYY) |  | End date (MM.YYYY) |
| D 3.2.1 |  | Deliverable |  |  |  | Target value |  | Delivery date (MM.YYYY) |
| A 3.3 |  | Activity description and partners involved [750 characters] Digital activity |  |  |  | Start date (MM.YYYY) |  | End date (MM.YYYY) |
| D 3.3.1 |  | Deliverable |  |  |  | Target value |  | Delivery date (MM.YYYY) |
| A 3.4 |  | Activity description and partners involved [750 characters] Public events |  |  |  | Start date (MM.YYYY) |  | End date (MM.YYYY) |
| D 3.4.1 |  | Deliverable |  |  |  | Target value |  | Delivery date (MM.YYYY) |
| A 3.5 |  | Activity description and partners involved [750 characters] Promotional material |  |  |  | Start date (MM.YYYY) |  | End date (MM.YYYY) |
| D 3.5.1 |  | Deliverable |  |  |  | Target value |  | Delivery date (MM.YYYY) |
| A 3.6 Media Relations |  | Activity Description and partners involved [750 characters] Media Relations |  |  |  | Start date (MM.YYYY) |  | End date (MM.YYYY) |
| D 3.6.1 |  | Deliverable |  |  |  | Target Value |  | Delivery date (MM.YYYY) |
| A 3.7 |  | Activity description and partners involved [750 characters] Final dissemination activity (mandatory) |  |  |  | Start date (MM.YYYY) |  | End date (MM.YYYY) |
| D 3.7.1 |  | Deliverable |  |  |  | Target value |  | Delivery date (MM.YYYY) |
| A 1.N |  | Activity description and partners involved [750 characters] Other type of Activity foreseen (max. 3) |  |  |  | Start Date (MM.YYYY) |  | End Date (MM.YYYY) |
| D 3.N.N |  | Deliverable |  |  |  | Target Value |  | Delivery date (MM.YYYY) |

Work Package Budget

For guidance regarding costs description please see work package 2.

| PP1 - Name | Staff cost (€) | Office and Administration (€) |  | Travel and Accommodation (€) |  | External Expertise and services (€) |  | Equipment (€) |  | Sub-total (€) |  | Revenues (€) | Total (€) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | [250 characters] | [250 characters] |  | [250 characters] |  | [250 characters] |  | [250 characters] |  | Automatically calculated |  | [250 characters] | Automatically calculated |
| Amount (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PP2 - Name | Staff cost (€) | Office and Administration (€) |  | Travel and Accommodation (€) |  | External Expertise and services (€) |  | Equipment (€) |  | Sub-total (€) |  | Revenues (€) | Total (€) |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Amount (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PP…X - Name | Staff cost (€) | Office and Administration (€) |  | Travel and Accommodation (€) |  | External Expertise and services (€) |  | Equipment (€) |  | Sub-total (€) |  | Revenues (€) | Total (€) |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Amount (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total (€) | Automatically calculated | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated | Automatically calculated |
| Indicative budget breakdown per year |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Year |  |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | Total |  |  |
| % budget |  |  |  |  |  |  |  |  |  |  | 100% |  |  |
| Amount EUR |  |  |  |  |  |  |  |  |  |  |  |  |  |

| WP Nr | WP title |  | WP start date | WP end date |  | WP budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 4-7 | IMPLEMENTATION |  | Automatic from activities | Automatic from activities |  | Automatic |  |
| Partners’ involvement |  |  |  |  |  |  |  |
| WP responsible partner |  |  |  |  |  |  |  |
| Other involved partners |  |  |  |  |  |  |  |
| Summary |  |  |  |  |  |  |  |
| [1500 Characters] Create maximum 4 Work Packages for implementation corresponding to the main pillars of your project. For the implementation work packages, clear cross-references should be made between the different work packages and if applicable a specific link to the investment work package. |  |  |  |  |  |  |  |
| Activities, outputs and deliverables |  |  |  |  |  |  |  |
| Activity A.4.1 | Activity title Example: A.4.1 Coaching and training |  |  |  | Start date (MM.YYYY) |  | End date (MM.YYYY) |
|  | Activity description and partners involved [750 characters] The description provided will mention the intermediary steps to develop the respective output; these steps will be reflected as deliverables structured in a logical chain. Please mention the partner(s) involved and their role in the activities. |  |  |  |  |  |  |
| D.4.1.1 ... O.4.1.1 | Deliverable or output description [250 characters] The deliverables of the activity mentioned above would be: D.4.1.1 Coaching interview D.4.1.2 Training session D.4.1.3 Feedback session The output of the activity mentioned above would be: O.4.1.1 Coaching and Training programme delivered Please mention which partner/s will be responsible for the delivery of each deliverable/output. Pay particular attention to quantification: in the description of the different deliverables/output provide the number of coaches to be recruited, the number of expected training sessions, the number of expected beneficiaries etc. If the deliverable is of a repetitive nature (i.e. training sessions) please include the delivery date of the last training. In the description specify the start date and when they are expected to be delivered in between (i.e. month 3 – month 4). |  |  |  | Target value |  | Delivery date (MM.YYYY) |
| Activity A.4.N | Activity title |  |  |  | Start date (MM.YYYY) |  | End date (MM.YYYY) |
|  | Activity description and partners involved [750 characters] |  |  |  |  |  |  |
| D / O 4.N.N | Deliverable or output description [250 characters] |  |  |  | Target value |  | Delivery date (MM.YYYY) |

Work Package Budget

For the costs description please see also work package 2.

| PP1 - Name | Staff cost (€) | Office and Administration (€) |  | Travel and Accommodation (€) |  | External Expertise and services (€) |  | Equipment (€) |  | Sub-total (€) |  | Revenues (€) | Total (€) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | [250 characters] | [250 characters] |  | [250 characters] |  | [250 characters] |  | [250 characters] |  | Automatically calculated |  | [250 characters] | Automatically calculated |
| Amount (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PP2 - Name | Staff cost (€) | Office and Administration (€) |  | Travel and Accommodation (€) |  | External Expertise and services (€) |  | Equipment (€) |  | Sub-total (€) |  | Revenues (€) | Total (€) |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Amount (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PP…X - Name | Staff cost (€) | Office and Administration (€) |  | Travel and Accommodation (€) |  | External Expertise and services (€) |  | Equipment (€) |  | Sub-total (€) |  | Revenues (€) | Total (€) |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Amount (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total (€) | Automatically calculated | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated | Automatically calculated |
| Indicative budget breakdown per year |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Year |  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  | Total |  |  |
| % budget |  |  |  |  |  |  |  |  |  |  | 100% |  |  |
| Amount EUR |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Indicative budget breakdown per Activity |  |  |
| --- | --- | --- |
| Activity | Amount (%) Please include the percentage that each activity represents in the work package (the total must be 100%) | Budget (€) Budget of each activity in EUR |
| A.4.1 |  |  |
| A.4.2 |  |  |
| A.4.X … |  |  |
| Total |  |  |

| WP investment | Title To the WP investment corresponds to 1 or more investments. |  | WP start date | WP end date | WP budget |
| --- | --- | --- | --- | --- | --- |
| Max 1 WP investment can be created |  |  | Automatic from activities | Automatic from activities | Automatic |
| Partners’ involvement |  |  |  |  |  |
| WP responsible partner |  | Drop-down list |  |  |  |
| Other partners involved |  | Drop-down list |  |  |  |
| Summary |  |  |  |  |  |
| [1500 Characters] Please describe the work package and the reasons for it, and why it is justified in the framework of the project. Bear in mind that stand-alone investments without clear added-value and not delivering against the initial objectives and expected results will not be supported. You can refer to the UIA guidance for more information. Ensure a clear cross-reference is made to the relevant implementation work packages (core project activities) in order to justify the reason of the investment. Is the investment crucial (main supporting element) for the success of the project? Does it correspond to the main output of the project, without which the expected result could not be achieved? Sustainability aspects related to the investment should be considered in this section. All investments should be described in detail. Descriptions of investments are similar to those for work packages as they contain activities, deliverables and outputs. Investments’ implementation should be in line with the overall project’s time plan. |  |  |  |  |  |
| Justification |  |  |  |  |  |
| [1500 Characters] Please clearly justify the need of your investment (link with objectives, implementation WP etc.). Investments should be proportionate to the work plan and budget, and should therefore represent good value for money. |  |  |  |  |  |

Work Package Budget

For the costs description please see work package 2. For more information regarding eligible investments costs, please refer to section 2.2 (Investment WP) of the UIA guidance. Considering the large costs often associated to investments and the rather limited space for description of the costs (250 characters per budget line), please do not hesitate to use the summary and description of the investment to further describe the concrete nature of the investment works.

| PP1 - Name |  | Staff cost (€) | Office and Administration (€) |  | Travel and Accommodation (€) |  | External Expertise and services (€) |  | Equipment (€) |  | Infrastructure and works | Sub-total (€) |  | Revenues (€) | Total (€) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  | Example (non-related to the example listed in the activities above) Personnel costs (7 social workers in total) for mentoring and coordinating A. 4.2.1 and for developing/ managing the online platform for language – self training courses. | Flat rate |  | [250 characters] Further information on the eligible costs under this budget line is to be found in the UIA guidance under section 4 For example: Participation of the staff to experts/ visit other similar initiatives ... |  | [250 characters] Further information on the eligible costs under this budget line is to be found in the UIA guidance under section 4 For example: External expertise to facilitate A.X.Y, workshops, translators, services of a designer, … |  | 3 laptops and 4 mobile phone for mentors. Furniture (table, chairs, desks etc.) for the urban lab. |  | [250 characters] Renovation works of … Purchase of … Construction and site preparation of … | Automatically calculated |  | Detail any cost related to revenue generating activity (sale or rent of a project good, payment of services, entrance or inscription fees for any event, …) directly paid by users. This budget line reduces accordingly the Total Eligible budget of the project e.g.: Rental income (200 EUR/ co-housing) for a 3 year period. Workshops inscriptions 50 EUR/person for 45 participants. | Automatically calculated |  |
| I.X.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Partner total (€) |  | Automatically calculated | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated | Automatically calculated |  | Automatically calculated | Automatically calculated |  |
| PP2 - Name |  | Staff cost (€) | Office and Administration (€) |  | Travel and Accommodation (€) |  | External Expertise and services (€) |  | Equipment (€) |  | Infrastructure and works | Sub-total (€) |  | Revenues (€) | Total (€) |  |
| Description |  | [250 characters] | [250 characters] |  | [250 characters] |  | [250 characters] |  | [250 characters] |  | [250 characters] | Automatically calculated |  | [250 characters] | Automatically calculated |  |
| I.X.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Partner total (€) |  | Automatically calculated | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated | Automatically calculated |  | Automatically calculated | Automatically calculated |  |
| PP…X - Name |  | Staff cost (€) | Office and Administration (€) |  | Travel and Accommodation (€) |  | External Expertise and services (€) |  | Equipment (€) |  | Infrastructure and works | Sub-total (€) |  | Revenues (€) | Total (€) |  |
| Description |  | [250 characters] | [250 characters] |  | [250 characters] |  | [250 characters] |  | [250 characters] |  | [250 characters] | Automatically calculated |  | [250 characters] | Automatically calculated |  |
| I.X.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Partner total (€) |  | Automatically calculated | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated | Automatically calculated |  | Automatically calculated | Automatically calculated |  |
| Total (€) |  | Automatically calculated | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated |  | Automatically calculated | Automatically calculated |  | Automatically calculated | Automatically calculated |  |
| Indicative budget breakdown per year |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Year |  |  | Year 1 |  | Year 2 |  | Year 3 |  | Year 4 |  |  | Total |  |  |
| Amount % |  |  |  |  |  |  |  |  |  |  |  | 100% |  |  |
| Budget (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Investment 1

| Investment title |  |
| --- | --- |
| The investment title will be considered as the output of this investment by the system (and therefore automatically included as such in the overall list of the outputs – section C.3.2 |  |
| Description of the investment |  |
| [1500 characters] Please describe the investment and clarify the link with the implementation work package(s) and overall project logic. Please include also the type of investment, information on the building site, major costs foreseen, relevant activities and studies to implement this work package. |  |
| Involved partners |  |
| Budget |  |

Locations of the investment

| Number | Country | NUTS 2 level | NUTS 3 level |
| --- | --- | --- | --- |
| 1 | To be selected from a drop-down menu | To be selected from a drop-down menu | To be selected from a drop-down menu |

| Investment risk |  |  |  |  |
| --- | --- | --- | --- | --- |
| [1500 characters] Description of the risks associated with the investment, go/no-go decisions, etc. plus mitigation actions and a contingency plan. Risks listed here should also be included/reflected in Part F of the Application Form (risks management section). |  |  |  |  |
| Investment documentation |  |  |  |  |
| [1500 characters] Please list all technical requirements and permissions (e.g. building permits) required for the investment according to the respective national legislation. Projects should indicate in detail if such permissions have already been acquired or when they can be expected. |  |  |  |  |
| Ownership |  |  |  |  |
| [1500 characters] As stated in the UIA guidance, “Ownership of outputs and results having the character of investments in infrastructure or productive investments realised within the project must remain with the concerned project partners for at least 5 years following the final payment to the Main Urban Authority” (to ensure the durability of the investment is in line with regulation). The following elements should be considered: - Who owns the site where the investment is located? - Who will retain ownership of the investment at the end of the project? - Who will take care of maintenance of the investment? How will this be done? |  |  |  |  |
| Activities, deliverables and outputs |  |  |  |  |
| Activity A.I.1 | Activity title | Start date (MM.YYYY) | End date (MM.YYYY) |  |
|  | Activity description and partners involved [750 characters] List here the different activities under this work package. Be aware that max. 5 activities can be listed per work package. Please follow the same guidance provided in the implementation Work Packages above. |  |  |  |
| D.I.1.1 | Deliverable description [250 characters] Please follow the same guidance provided in the implementation Work Packages above. | Target value | Delivery date (MM.YYYY) |  |
| Activity A.I.2 | Activity title | Start date (MM.YYYY) | End date (MM.YYYY) |  |
|  | Activity description and partners involved [750 characters] |  |  |  |
| D.I.2.1 | Deliverable description [250 characters] | Target value | Delivery date (MM.YYYY) |  |
| Activity A.I.N | Activity title | Start date (MM.YYYY) | End date (MM.YYYY) |  |
|  | Activity description and partners involved [750 characters] |  |  |  |
| D.I.N.1 | Deliverable description [250 characters] | Target value | Delivery date (MM.YYYY) |  |

Investment N°: please add as many investments as needed

| WP Nr. | WP title |  | WP start date | WP end date | WP budget |
| --- | --- | --- | --- | --- | --- |
| Last WP (X) | Closure and knowledge transfer |  | Automatic from activities | Automatic from activities | 15,000 |
| Partners’ involvement |  |  |  |  |  |
| WP responsible partner |  |  |  |  |  |
| Involved associated urban authority and/or key stakeholder |  |  |  |  |  |
| Summary [1500 characters] |  |  |  |  |  |
| Describe how: - The project will carry out the administrative closing procedure - The project will ensure that the final lessons learnt will be transferred to other organization Lump sum of EUR 15.000 will be paid when all compulsory deliverables are provided and accepted Please note that the UIA Experts should support the Main Urban Authority with the knowledge transfer. |  |  |  |  |  |
| Activities and deliverables |  |  |  |  |  |
| Activity X.1 | Activity title List here the different activities under this Work Package. Typical activities for this Work Package are for instance the procedure for the administrative closure of the project including production of final payment claim and final progress report, final certification of costs, etc. Please note that 1 activity has to be exclusively devoted to the Transfer Knowledge activities that include the production of the final qualitative report |  |  | Start date (MM.YYYY) | End date (MM.YYYY) |
|  | Activity description and partners involved [750 characters] |  |  |  |  |
| D X.1.1 | Deliverable [250 characters] |  |  | Target value | Delivery date (MM.YYYY) |
| Activity X.2 | Activity title Transfer of knowledge activities (Activity partially pre-filled) |  |  | Start date (MM.YYYY) | End date (MM.YYYY) |
|  | Activity description - Production of the final qualitative report - Participation in national/transnational conferences to share the final lessons learnt - Other activities for knowledge transfer |  |  |  |  |
| D X.2.1 | Deliverable - Final qualitative report |  |  | Target value | Delivery date 1 year following project end date |
| D X.2.2 | Deliverable |  |  | Target value | Delivery date 1 year following project end date |
| Activity X.3 | Activity title Administrative closure (Activity pre-filled) |  |  | Start date (MM.YYYY) | End date (MM.YYYY) |
|  | Activity description - Preparation and submission of final progress report |  |  |  |  |
| D X.2.1 | Deliverable - Final progress report |  |  | Target value | Delivery date 3 months following project end date |

Work Package Budget

| Partner Name | Staff cost (€) | Office and Administration (€) | Travel and Accommodation (€) | External Expertise and services (€) | Equipment (€) | Infrastructure and works | Sub-total (€) | Revenues (€) | Total (€) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 15,000.00 |  |  |  |  | Automatically calculated |

E. Project budget section

Section automatically generated from the Work Plan

| E.1 Project Budget Co-Financing Source (Fund) - breakdown per partner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Partner |  | Country |  |  | ERDF co-financing (80% ERDF) |  |  |  |  |  | Contribution (at least 20% should be ensured by each project partner) |  |  |  |  |  |  |  |  | Total 100% TEC |  |  |  |  |  |
|  |  |  |  |  | EUR |  |  | ERDF rate |  |  | Public |  |  | Private |  |  | Total |  |  | Budget |  |  |  | % of project budget |  |
| PP1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PP2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PPn |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.2 Project budget - Overview per partner / per period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Partner |  |  |  |  | 2015 |  | 2016 |  |  |  | 2017 |  |  | 2018 |  |  | … |  |  | 2024 |  |  |  | Total |  |
| PP1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PP2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PPn |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.3 Project budget - Overview per partner / per work package |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Partner |  |  |  |  | WP1 |  | WP2 |  |  |  | WP3 |  |  | WP4 |  |  | … |  |  | WPn |  |  |  | Total |  |
| PP1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PP2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PPn |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % of total budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.4 Project Budget - Overview per Work Package / per Period |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP |  |  |  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  |  | Total |  |  |  |
| WP1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WPn |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % of total budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.5 Project Budget- Overview per partner / per budget line |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Partner |  |  | Staff |  | Office and administration |  |  |  | Travel and accommodation |  | External expertise and services |  |  | Equipment |  |  | Infrastructure and construction works | Sub-total |  |  |  | Revenues |  | Total |
| PP1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PP2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PP3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PPn |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % of total budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| E.6 Project Budget- Overview per Work Package / per budget line |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work Package |  |  | Staff |  | Office and administration |  |  |  | Travel and accommodation |  | External expertise and services |  |  | Equipment |  |  | Infrastructure and construction works | Sub-total |  |  |  | Revenues |  | Total |
| WP1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WP3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| … |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| WPn |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total (€) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| % of total budget |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PART F – Source(s) of partners’ contribution

PP1 – Name of the Partner

| Name of the Organisation/ Source of Contribution | Legal Status | % of Total Partner Contribution | Amount (€) | Cash or in-Kind contribution | Comment |
| --- | --- | --- | --- | --- | --- |
| … |  |  |  |  |  |
| … |  |  |  |  |  |
| Total (€) |  |  |  |  | Contribution Target: This is automatically calculated by the system |

PP2 – Name of the Partner

| Name of the Organisation/ Source of Contribution | Legal Status | % of Total Partner Contribution | Amount (€) | Cash or in-Kind contribution | Comment |
| --- | --- | --- | --- | --- | --- |
| … |  |  |  |  |  |
| … |  |  |  |  |  |
| Total (€) |  |  |  |  | Contribution Target: This is automatically calculated by the system |

…

PPn– Name of the Partner

| Name of the Organisation/ Source of Contribution | Legal Status | % of Total Partner Contribution | Amount (€) | Cash or in-Kind contribution | Comment |
| --- | --- | --- | --- | --- | --- |
| … |  |  |  |  |  |
| … |  |  |  |  |  |
| Total (€) |  |  |  |  | Contribution Target: This is automatically calculated by the system |

Part G – Risk management

| Description of the risk | Impact | Likelihood |  | Actions to mitigate the risk |
| --- | --- | --- | --- | --- |
| [500 characters] Please describe your risk/s and add as many risks as necessary. Please list any risk that may affect the project implementation, you are reminded that those risks for Investment when applicable should also be included here. As an example: Project management related risks (partners withdrawal, staff issues, …) Contracting (External experts) Delays in implementation of the activities and deliverables … | - Incident - Minor - Serious - Major - Catastrophic |  | - Improbable - Remote - Possible - Probable - Likely | [500 characters] Please provide a clear and detailed description of the action/s that will be taken in order to mitigate the potential risk. For example. In case a partner withdraws, the MUA would ensure a re-distribution of tasks and look for external expertise support for those tasks that are unable to be covered by the partnership); |

The typology of risks can be divided into the following areas:

a. Strategic – relating to the rationale, quality and timely delivery of the project objective, final result or the main project outputs (e.g. project results not achievable, major difficulties in delivering key project outputs);

b. Technology or innovativeness – linked to the development or implementation of innovative technology or solutions; Intellectual Property Rights should also be thoroughly considered;

c. Action plan – related to the sequencing of individual activities and how this affects other parts of the work plan; the adequacy of the time required for each activity – realism of the delivery timetable; the parameters determining whether an activity can be implemented; underperformance of individual partners or partnership as a whole; qualitative and quantitative modifications to the project deliverables that might affect the main project outputs; modifications in the type and scope of activities, etc.;

d. Investment plan – linked to the investment delivery stages (feasibility study, permits and agreements including political approval and planning, procurement – including unsuccessful procurement, types of works to be undertaken), ownership or durability issues as well as Intellectual Property Rights, etc.;

e. Procurement – apart from the investment angle mentioned above – linked to the involvement of external experts or consultants in project implementation (e.g. externalized project management, etc.);

f. Communication and engagement – potentially ineffective project communication strategy with internal or external effects (e.g. on target groups or stakeholders and hence on the quality of outputs or deliverables) etc.;

g. Finance – linked to match-funding required for the project, funding schemes foreseen etc.

Part H – Urban Authority confirmation

By signing the application form the (Main) Urban Authority hereby confirms that:

- the project neither in whole nor in part has or will receive any other complementary EU funding (except for the funding indicated in this application form) during the whole duration of the project;

- The Main Urban Authority and the Associated Urban Authorities (if any) are not involved in other project proposals in the framework of the present Call for Proposals

- The project partners listed in the application form are committed to take part in the project’s activities and financing;

- The project is in line with the relevant EU and national legislation and policies of the countries involved;

- The Urban Authority and the project partners will act according to the provisions of the relevant national and EU regulations, especially regarding structural funds, public procurement, state aid, environment and equal opportunities, as well as the specific provisions of the UIA Initiative;

- The information in the Application Form is accurate and true to the best knowledge of the Urban Authority.

| Name of person signing |  |
| --- | --- |
| Position of person signing |  |
| Place and date |  |
| Signature and stamp of lead partner (if exists) |  |

In Part H, all applicants must upload a signed confirmation sheet. Please note, the confirmation sheet template can be downloaded at any time and must be uploaded before the closure of the Call for Proposals (in a scanned or .pdf version).